## Best Case Chart
Yelp Recommender
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Initiation |  |  |  |  | 0%
Describe Product | 1 | 2 |  |  | 0%
Develop Marketing Strategy | 1 | 3 |  |  | 0%
Design Brochure | 3 | 2 |  |  | 0%
Software Development |  |  |  |  | 0%
Requirements Analysis | 3 | 1 |  |  | 0%
Software Design | 4 | 3 |  |  | 0%
System Design | 4 | 3 |  |  | 0%
Coding | 6 | 5 |  |  | 0%
Write Documentation | 10 | 1 |  |  | 0%
Unit Testing | 10 | 2 |  |  | 0%
System Testing | 12 | 2 |  |  | 0%
Package Deliverables | 13 | 1 |  |  | 0%
Roll out |  |  |  |  | 0%
Survey Potential Market | 4 | 4 |  |  | 0%
Develop Pricing Plan | 13 | 2 |  |  | 0%
Develop Implementation Plan | 13 | 1 |  |  | 0%
Write Client Proposal | 15 | 3 |  |  | 0%

## Best Case Values
Activity | Start Time | End Time | Duration
A | 1 | 2.33 | 2
B | 1 | 3.67 | 3
C | 2.33 | 3.66 | 2
D1 | 2.33 | 3.22 | 1
D2 | 3.22 | 5.44 | 3
D3 | 3.22 | 5.44 | 3
D4 | 5.44 | 9.88 | 5
D5 | 9.88 | 10.77 | 1
D6 | 9.88 | 11.21 | 2
D7 | 11.21 | 12.54 | 2
D8 | 12.54 | 12.98 | 1
E | 3.67 | 6.84 | 4
F | 12.98 | 14.31 | 2
G | 12.98 | 13.98 | 1
H | 14.31 | 16.98 | 3

## Expected Chart
Yelp Recommender
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Initiation |  |  |  |  | 0%
Describe Product | 1 | 3 |  |  | 0%
Develop Marketing Strategy | 1 | 4 |  |  | 0%
Design Brochure | 3.67 | 3 |  |  | 0%
Software Development |  |  |  |  | 0%
Requirements Analysis | 3.67 | 2 |  |  | 0%
Software Design | 5 | 4 |  |  | 0%
System Design | 5 | 4 |  |  | 0%
Coding | 8.33 | 6 |  |  | 0%
Write Documentation | 13.89 | 2 |  |  | 0%
Unit Testing | 13.89 | 3 |  |  | 0%
System Testing | 16.11 | 3 |  |  | 0%
Package Deliverables | 18 | 1 |  |  | 0%
Roll out |  |  |  |  | 0%
Survey Potential Market | 6.34 | 6 |  |  | 0%
Develop Pricing Plan | 19.22 | 3 |  |  | 0%
Develop Implementation Plan | 19.22 | 2 |  |  | 0%
Write Client Proposal | 21.89 | 4 |  |  | 0%

## Expected Values
Activity | Start Time | End Time | Duration
A | 1 | 3.67 | 3
B | 1 | 5 | 4
C | 3.67 | 6.34 | 3
D1 | 3.67 | 5 | 2
D2 | 5 | 8.33 | 4
D3 | 5 | 8.33 | 4
D4 | 8.33 | 13.89 | 6
D5 | 13.89 | 15.67 | 2
D6 | 13.89 | 16.11 | 3
D7 | 16.11 | 18.33 | 3
D8 | 18.33 | 19.22 | 1
E | 6.34 | 11.67 | 6
F | 19.22 | 21.89 | 3
G | 19.22 | 20.55 | 2
H | 21.89 | 25.89 | 4

## Worst Case Chart
Yelp Recommender
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66
Initiation |  |  |  |  | 0%
Describe Product | 1 | 4 |  |  | 0%
Develop Marketing Strategy | 1 | 6 |  |  | 0%
Design Brochure | 5 | 4 |  |  | 0%
Software Development |  |  |  |  | 0%
Requirements Analysis | 5 | 2 |  |  | 0%
Software Design | 6.78 | 5 |  |  | 0%
System Design | 6.78 | 5 |  |  | 0%
Coding | 11.22 | 7 |  |  | 0%
Write Documentation | 17.89 | 3 |  |  | 0%
Unit Testing | 17.89 | 4 |  |  | 0%
System Testing | 21.22 | 4 |  |  | 0%
Package Deliverables | 24.55 | 2 |  |  | 0%
Roll out |  |  |  |  | 0%
Survey Potential Market | 9 | 8 |  |  | 0%
Develop Pricing Plan | 25.88 | 4 |  |  | 0%
Develop Implementation Plan | 25.88 | 2 |  |  | 0%
Write Client Proposal | 29.88 | 6 |  |  | 0%

## Worst Case Values
Activity | Start Time | End Time | Duration
A | 1 | 5 | 4
B | 1 | 6.33 | 6
C | 5 | 9 | 4
D1 | 5 | 6.78 | 2
D2 | 6.78 | 11.22 | 5
D3 | 6.78 | 11.22 | 5
D4 | 11.22 | 17.89 | 7
D5 | 17.89 | 20.56 | 3
D6 | 17.89 | 21.22 | 4
D7 | 21.22 | 24.55 | 4
D8 | 24.55 | 25.88 | 2
E | 9 | 17 | 8
F | 25.88 | 29.88 | 4
G | 25.88 | 27.55 | 2
H | 29.88 | 35.21 | 6